## APP-GNGWN-PPRA
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - SUBMISSION TO PPRA
Name of Procuring Entity:
FINANCIAL YEAR
Description | Tender No. | Lot Number | BASIC DATA |  | Gen. Proc Notice Advert | PRE-QUALIFICATION |  |  | INVITATION AND AWARD OF TENDER
|  |  | Estimated Amount in '000 Tshs | Procurement Method |  | Invitation Date | Closing-Opening | Notification of Applicants | Tender Invitation Date | Tender Closing-Opening | Approval Eval Report | Notice of intention to award Date | Vetting/ Ratification of contracts | Award Notification Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Total Cost

## APP-GNGWN-EU
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - EXTERNAL USE
Name of Procuring Entity:
FINANCIAL YEAR
Description | Tender No. | Lot Number | Procurement Method | PRE-QUALIFICATION |  |  | Invitation for Tenders and contract signature
|  |  |  | Invitation Date | Closing-Opening | Notification of Applicants | Tender Invitation Date | Tenders Closing-Opening | Notice of intention to award Date | Vetting/ Ratification of contracts | Notification of Award
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12

## APP-GNCONS-GFU
PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines on Filling the Procurement Plan Template for Consultancy Services
1. | An Annual Procurement Plan (APP) is a mandatory feature of the procurement policy framework as articulated in PPA 2011. The approval of APP in a meeting of Budget Approving Authority of a PE can be used to achieve the requirement that all procurement must have the approval of the Budget Approving Authority. It can further be used as a monitoring tool to ensure that all planned procurement follow the procedures and target dates.
2. | The Procurement Plan Template for Consultancy Services has been prepared to fulfill the requirements of Section 49 of the PPA 2011 and Regulation 69 of GN. 446 of 2013.
3. | Three kinds of APP Templates are introduced in this Guideline as shown below. A Soft Copy of the Guideline is contained in a Worksheet designated as APP-CONSULTANTS-GFU.
| 3.1 | Template of APP for Internal Use: This Template is contained in a Worksheet designated as APP-GN446 -IU. It gives detailed information about each procurement to be carried out by a PE including key dates for which certain actions must be completed by its staff to ensure that there is no delay in the procurement process. For each tender, two rows are provided: one for recording the planned dates for various actions and one for filling in actual dates when the actions were implemented.
| 3.2 | Template of APP for External Use: This Template is contained in a Worksheet designated as APP-GN446 -EU. It gives detailed information about each procurement to be carried out by a PE through open competition and it forms part of the GPN to be made available to potential consultants. It aims at notifying potential consultants of procurement opportunities available in a PE. In this template information regarding particulars of the assignments, dates for advertisement, dates for invitation to submit proposals and notification of consultants are given.
| 3.3 | Template of APP for Submission to PPRA: This Template is contained in a Worksheet designated as APP-GN446 -PPRA. It gives detailed information about each procurement to be carried out by a PE including key dates for notifying potential consultants of the tender proceedings and results of the tender process. This is required to be submitted to PPRA at the start of the financial year to enable PPRA be aware of the procurement volume for that particular year and enable it plan its monitoring activities accordingly.
4. | Abbreviations used in this Guideline
| APP | Annual Procurement Plan
| FP | Financial Proposal
| GN 446 | The Public Procurement Regulations, GN. No. 446 of 2013
| GPN | General Procurement Notice
| PE | Procuring Entity
| PMU | Procurement Management Unit
| PPA 2011 | Public Procurement Act No. 7 of 2011
| PPRA | Public Procurement Regulatory Authority
| RFP | Request for Proposal
| TB | Tender Board
| TP | Technical Proposal
Column No. | Guidance on the Information to be filled in the respective column of the Template |  | Corresponding Column in the APP Template for External Use | Corresponding Column in the APP Template for Submission to PPRA
01-06 | These columns gives details of various tenders to be floated by the PE, their estimated values and selected procurement methods |  | 01-06 | 01-04
01. | This column shall include a brief description of the Consultancy Assignment e.g. Consultancy Services for Carrying Out Detailed Design for Rehabilitation of XXX Road |  | 01 | 01
02. | This column shall include the designated tender number. For easy identification of the PEs, PPRA shall issue code numbers to identify each PE. The tender number shall be preceded by the code number of the PE and the respective financial year. For example, if the code number of the PE is P01 and the financial year is 2013/14 the tender numbers shall be preceded by P01-2013/14- |  | 02 | 02
03. | This column shall indicate lot numbers in case of a tender divided into lots. When there is only one lot, this shall be shown in this column as a single lot. |  | 03 | 03
04. | This column shall indicate the estimated value of the procurement for each lot. The estimated value shall to a large extent reflect the budgeted amount for that procurement. To assist PEs to prepare correct estimates, the Research and Documentation Section of PPRA shall prepare price indices for various items based on consultancy assignments carried out in the previous years. |  | This information is not required for disclosure to the potential tenderers as it will tend to influence prices | 04
05. | Procurement Method to be adopted shall be shown in this column. Determination of the appropriate method shall be guided by Part IX - Procedures for Selection and Employment of Consultants of GN. 446. |  | 04 | 05
06 | In this column the method of selection adopted shall be given. Determination of the appropriate selection method shall be done in accordance with Part IX - Procedures for Selection and Employment of Consultants of GN. 446 |  | 05 | 06
07 | Indicate the selected type of contract in accordance with PartIX - Procedures for Selection and Employment of Consultants of GN. 446. |  | 06 | 07
08 | For tenders where open competitive methods have been found to be appropriate, they shall be advertised in the GPN. The date earmarked for the GPN shall be shown in this column. To cut down on the costs of advertising, the PE should consider using a minimum number of GPN consisting of several tenders. |  | This is not required since the whole of this document consist GPN | 08
09-12 | These columns apply for Tenders where Invitation of Expression of Interest need to be carried out prior to inviting tenders. |  | 07-09 | 09-11
09. | This column shall indicate the date when the PE expects to advertise for the Invitation for Expression of Interest |  | 07 | 09
10. | This column shall indicate the expected deadline for the submission and opening of the Expression of Interest entries. Statutory periods from the date of advertising to the submission of the applications are given in the Twelfth Schedule of GN. 446. They are 30 days and 14 days for the international and national competitive selection respectively. |  | 08 | 10
11. | In this column, the PE shall indicate the deadline by which the evaluation of Expression of Interest entries must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
12. | This column indicates the deadline by which the Expression of Interest evaluation report must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. |  | 09- The successful applicants must be immediately be informed after the approval of shortlist is done by the TB | 11
13-21 | These columns gives the details of the actual tender process starting from the preparation of tendering documents to the approval of award of contract. |  | 10-12 | 12-15
13. | In this column, the PE shall indicate the deadline by which the RFP Document must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.This deadline may be in parallel with deadlines for actions under those columns 09 to 12. |  | This information is for internal use to the PE
14. | This column indicates the deadline by which the RFP Document must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. The approval of the document can be delegated to the PMU. In cases of tenders with Invitation for Expression of Interest, in order to avoid delays, this date could the same as that appearing in column 12
15. | This column shall indicate the date when the PE expects to issue of RFP documents to the shortlisted consultants. |  | 10 | 12
16. | This column shall indicate the expected deadline for the submission and opening of the RFP. Statutory periods from the date of invitation to the submission of the proposals are given in the Twelfth Schedule of GN. 446. They are 45 days and 30 days for the international and national competitive selection respectively. |  | 11 | 13
17. | In this column, the PE shall indicate the deadline by which the evaluation of TP must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
18. | This column indicates the deadline by which the TP evaluation report must be approved by the TB.
19. | This column indicates the set date for opening of FP. Normally it is two weeks from the date specified in Column 18. A shorter period may be fixed if all Consultants have qualified to have their FP opened and have confirmed to attend the opening meeting
20. | This column indicates the deadline by which the Combined evaluation report must be completed. |  | This information is for internal use to the PE
21. | This column indicates the deadline by which the combined evaluation report must be approved by TB |  | 22- The all bidders must immediately be informed after the decision of contract award is done by the TB to commence the 14 day window for compalnts | 14/15
23-25 | These columns gives the details of the final actions towards formalization of the contract.
23 | In this column the amount of the contract award shall be inserted. In the planned row it is expected to insert the estimated (budgeted amount) of the particular tender. In the actual row PE shall insert the amount of the contract award approved by the TB |  | This information is for internal use to the PE. However PPRA shall obtain the award information on the Reports to be submitted on the implementation of each procurement
24 | In this column the PE shall fill in the expected date for contract for contract award. For planning purposes this date shall be the determinant of the dates by which the preceding actions must be completed so that the award of the contract is made by this date
25 | In this column the PE shall fill in the expected date for signing of the contract.
For More Information and Guidance, Contact
Chief Executive Officer,
Public Procurement Regulatory Authority
PPF Tower, 8th Floor
P.O. Box 49, Dar-es-Salaam
Tel. No. +255 22 2121236/7, 2133466
Fax. No. +255 22 2121238
E-mail: ceo@ppra.go.tz
Website: www.ppra.go.tz

## APP-GNGWN-GFU
PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines on Filling the Procurement Plan Template for Goods, Works and Non-Consultancy Services
1. | An Annual Procurement Plan (APP) is a mandatory feature of the procurement policy framework as articulated in PPA 2011. The approval of APP in a meeting of Budget Approving Authority of a PE can be used to achieve the requirement that all procurement must have the approval of the Budget Approving Authority . It can further be used as a monitoring tool to ensure that all planned procurement follow set procedures and target dates.
2. | The Procurement Plan Template for Goods, Works and Non-Consultancy Services has been prepared to fulfill the requirements of Section 49 of the PPA 2011 and Regulation 69 of GN. 446 of 2013.
3. | Three kinds of APP Templates are introduced in this Guideline as shown below. A Soft Copy of the Guideline is contained in a Worksheet designated as APP-GN97-GFU.
| 3.1 | Template of APP for Internal Use: This Template is contained in a Worksheet designated as APP-GN446 -IU. It gives detailed information about each procurement to be carried out by a PE including key dates for which certain actions must be completed by its staff to ensure that there is no delay in the procurement process. For each tender, two rows are provided: one for recording the planned dates for various actions and one for filling in actual dates when the actions were implemented.
| 3.2 | Template of APP for External Use: This Template is contained in a Worksheet designated as APP-GN446 -EU. It gives detailed information about each procurement to be carried out by a PE through open competition and it forms part of the GPN to be made available to potential bidders. It aims at notifying potential bidders of procurement opportunities available in a PE. In this template information regarding particulars of tender, dates for advertisement and notification of bidders are given.
| 3.3 | Template of APP for Submission to PPRA: This Template is contained in a Worksheet designated as APP-GN446 -PPRA. It gives detailed information about each procurement to be carried out by a PE including key dates for notifying potential bidders of the tender proceedings and results of the tender process. This is required to be submitted to PPRA at the start of the financial year to enable PPRA be aware of the procurement volume for that particular year and enable to plan its monitoring activities accordingly.
4. | Abbreviations used in this Guideline
| APP | Annual Procurement Plan
| GN. 446 | The Public Procurement Regulations, GN. No.446 of 2013
| GPN | General Procurement Notice
| PE | Procuring Entity
| PMU | Procurement Management Unit
| PPA 2011 | Public Procurement Act No. 7 of 2011
| PPRA | Public Procurement Regulatory Authority
| TB | Tender Board
Column No. | Guidance on the Information to be filled in the respective column of the Template |  | Corresponding Column in the APP Template for External Use | Corresponding Column in the APP Template for Submission to PPRA
01-06 | These columns gives details of various tenders to be floated by the PE, their estimated values and selected procurement methods |  | 01-04 | 01-04
01. | This column shall include a brief description of the Tender e.g. Tender for the Supply of Office Stationery |  | 01 | 01
02. | This column shall include the designated tender number. For easy identification of the PEs, PPRA shall issue code numbers to identify each PE. The tender number shall be preceded by the code number of the PE and the respective financial year. For example, if the code number of the PE is P01 and the financial year is 2013/14, the tender numbers shall be preceded by P01-2013/14- |  | 02 | 02
03. | This column shall indicate lot numbers in case of a tender divided into lots. When there is only one lot, this shall be shown in this column as a single lot. |  | 03 | 03
04. | This column shall indicate the estimated value of the procurement for each lot. The estimated value shall to a large extent reflect the budgeted amount for that procurement. To assist PEs to prepare correct estimates, the Research and Documentation Section of PPRA shall prepare price indices for various items based on tenders carried out in the previous years. |  | This information is not required for disclosure to the potential bidders as it will tend to influence prices | 04
05. | Procurement method to be adopted shall be shown in this column. Determination of the appropriate method shall be guided by Part III - Procedures for Procurement of Goods Works and Non-Consultant Services of GN. 446. |  | 04 | 05
06. | For tenders where open tendering methods have been found to be appropriate, they shall be advertised in the GPN. The date earmarked for the GPN shall be shown in this column. To cut down on the costs of advertising, the PE should consider using a minimum number of GPN consisting of several tenders. |  | This is not required since the whole of this document consist GPN | 06
07-12 | These columns apply for Tenders where pre-qualification of bidders need to be carried out prior to inviting tenders. |  | 05-07 | 07-09
07. | In this column, the PE shall indicate the deadline by which pre-qualification documents must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
08. | This column indicates the deadline by which pre-qualification documents must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. The approval of the documents can be delegated to the PMU.
09. | This column shall indicate the date when the PE expects to advertise for the pre-qualification process. |  | 05 | 07
10. | This column shall indicate the expected deadline for the submission and opening of the pre-qualification entries. Statutory periods from the date of advertising to the submission of the applications are given in the Eight Schedule of GN.446. They are 30 days and 21 days for the international and national competitive bidding respectively. |  | 06 | 08
11. | In this column, the PE shall indicate the deadline by which the evaluation of pre-qualification entries must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
12. | This column indicates the deadline by which the pre-qualification evaluation report must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. This shall also be the date for notifications of the outcome of the pre-qualification process. |  | 07- The successful applicants must be immediately be informed after the approval of shortlist is done by the TB | 09
13-18 | These columns gives the details of the actual tender process starting from the preparation of bidding documents to the approval of award of contract. |  | 08-10 | 10-13
13. | In this column, the PE shall indicate the deadline by which the Tender Document must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.This deadline may be in parallel with deadlines for actions under columns 07 to 12. |  | This information is for internal use to the PE
14. | This column indicates the deadline by which the Tender Document must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. The approval of the document can be delegated to the PMU. In cases of tenders with pre-qualification, in order to avoid delays, this date could the same as that appearing in column 12
15. | This column shall indicate the date when the PE expects to advertise for the tender or to start to issue tender documents to the shortlisted bidders in the case of a tender with pre-qualification. |  | 08 | 10
16. | This column shall indicate the expected deadline for the submission and opening of the tenders. Statutory periods from the date of advertising to the submission of tenders are given in the Eighth Schedule of GN. 446. They are 45 days and 30 days for the international and national competitive bidding respectively. Where large works are involved this shall be at least 90 days. |  | 09 | 12
17. | In this column, the PE shall indicate the deadline by which the evaluation of tenders must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
18. | This column indicates the deadline by which the tender evaluation report must be approved by the TB. This shall also be the date for notifying the winner. |  | 12 | 13
19 | In this column the PE shall fill in the expected date of Notice of intention to award. All bidders must immediately be informed after the decision of contract award is done by the TB to commence the 14 day window for complaints |  | 10 | 13
20 | In this column the PE shall fill in the expected date of submission of a draft contract for Vetting by the Attorney General or date of submission of a draft contract for Ratification by Legal Officer of a procuring entity. The accounting officer shall, within three working days after being notified by the tender board of its award decision for award acceptance whose value is fifty million shillings or more, submit to the Attorney General the draft contract for vetting and review within twenty one working days upon receiving it. Acceptance of tender whose value is below fifty million shillings shall be vetted by a legal officer of a procuring entity before it is signed by the parties and vet the draft contract within fourteen working days upon receiving it. |  | 11 | 14
21-23 | These columns gives the details of the final actions towards formalization of the contract.
21 | In this column the amount of the contract award shall be inserted. In the planned row it is expected to insert the estimated (budgeted amount) of the particular tender. In the actual row PE shall insert the amount of the contract award approved by the TB |  | This information is for internal use to the PE. However PPRA shall obtain the award information on the Reports to be submitted on the implementation of each procurement
22 | In this column the PE shall fill in the expected date for contract for contract award. For planning purposes this date shall be the determinant of the dates by which the preceding actions must be completed so that the award of contract is made by this date
23 | In this column the PE shall fill in the expected date for signing of the contract.
For More Information and Guidance, Contact
Chief Executive Officer,
Public Procurement Regulatory Authority
PPF Tower, 8th Floor
P.O. Box 49, Dar-es-Salaam
Tel. No. +255 22 2121236/7, 2133466
Fax. No. +255 22 2121238
E-mail: ceo@ppra.go.tz
Website: www.ppra.go.tz

## NON-CONSULTANCE INTERNAL
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - INTERNAL USE
Name of Procuring Entity:
FINANCIAL YEAR 2017-2018
Description | Tender No. | Lot Number | BASIC DATA |  | Gen. Proc Notice Advert | PRE-QUALIFICATION |  |  |  | PRE-QUALIFICATION |  | TENDERING DOCUMENTS |  | Invitation for Tenders and Evaluation | [5 empty] | Contract Finalization |  |  | Plan vs. Actual
[6 empty] | DOCUMENT |  | INVITATION |  | EVALUATION |  |  |  | Invitation for Tenderding |  | Tender Evaluation and approval of award
|  |  | Estimated Amount in '000 Tshs | Procurement Method |  | Preparation by PMU | Approval by TB | Invitation Date | Closing-Opening | Submission Eval Rpt | Approval by TB | Prep & Submission by PMU | Approval by TB | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Approval by TB | Notice of intention to award Date | Vetting/ Ratification of contracts | Contract Amount in Tshs. 000 | Date Contract Award | Date Contract Signature
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
GOODS
SUPPLY OF OFICE CONSUMABLE AND COMPUTER ACCESSORY | LGA/049/G/2017/2018/01 | LOT I-Supply of office consumable | 110944695.65 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT-II-supply of Computr ,Fax macine Scana,Printer and accesory | 31992269 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF FUEL AND LUBRICANT | LGA/049/G/2017/2018/02 | LOT I-Supply of diesel | 218620402.99 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT II- Supply of kerosine | 1076600 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA
SUPPLY OF FUEL |  | LOT III- Supply of Petrol | 32385458 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT IV- Supply of lubricant | 400000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF BUILDING MATERIA ,CLEAN SUPPLIES, AND PROTECTIVE GEAR | LGA/049/G/2017/2018/03 | LOT-I Supply of building material | 2621751662 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT-II Supply of Clean material | 23958992 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF TRAINNING MATERIALS | LGA/049/G/2017/2018/04 | LOT -I SUPPLIES OF TRAINNING MATERIALS | 23958992 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF TYRE, BATTERY, SPARE PART & ELECTRONICS/ELECTRICAL PARTS | LGA/049/G/2017/2018/05 | SUPPLY OF TYRE, BATTERY, SPARE PART & ELECTRONICS/ELECTRICAL PARTS | 2669669646 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF UNIFORM AND SPORTING SUPPLIES | LGA/049/G/2017/2018/06 | SUPPLY OF UNIFORM AND SPORTING SUPPLIES | 24550000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF FUNITURE & FITTINGS | LGA/049/G/2017/2018/07 | LOT I-SUPPLY OF FUNITURE & FITTINGS | 24133136 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF INFORMATION, COMMUNICATION & TECHNOLOGY EQUIPMENTS | LGA/049/G/2017/2018/08 | SUPPLIES OF INFORMATION, COMMUNICATION & TECHNOLOGY EQUIPMENTS | 9188533.96 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF DESK TABLE AND CHAIR | LGA/049/G/2017/2018/09 | SUPPLIES OF DESK TABLE AND CHAIR | 12500000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
PROVISION OF PROTECTIVE CLOTHEING FOOTWEAR AND GEARS | LGA/049/G/2017/2018/10 | PROVISION OF PROTECTIVE CLOTHEING FOOTWEAR AND GEARS | 1000000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF SPECIALIZED EQUIPMENT & SMALL TOOLS | LGA/049/G/2017/2018/11 | SUPPLIES OF SPECIALIZED EQUIPMENT & SMALL TOOLS | 50910500 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF TECHNICAL MATERIALS | LGA/049/G/2017/2018/12 | SUPPLIES OF TECHNICAL MATERIALS | 7650000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF NEWSPAPER & MAGAZINES AND BOOKS,REFERENCES & PERIODIC BOOKS | LGA/049/G/2017/2018/13 | SUPPLIES OF NEWSPAPER & MAGAZINES AND BOOKS,REFERENCES & PERIODIC BOOKS | 1979722 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF ARMS & AMMUNATIONS | LGA/049/G/2017/2018/14 | SUPPLIES OF ARMS & AMMUNATIONS | 500000 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF MOTORCLE /MOTOR VEHICLE | LGA/049/G/2017/2018/15 | SUPPLIES OF MOTORCLE /MOTOR VEHICLE | 183000000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF PHOTOGRAPHIC EQUIPMENT | LGA/049/G/2017/2018/16 | SUPPLY OF PHOTOGRAPHIC EQUIPMENT | 40099900 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF TV AND RADIO EQUIPMENT AND PULICITY | LGA/049/G/2017/2018/17 | SUPPLY OF TV AND RADIO EQUIPMENT AND PULICITY | 5700000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF VETINARY , SEEDS, AND AGRICULTURAL MATERIAL | LGA/049/G/2017/2018/18 | SUPPLY OF VETINARY , SEEDS, AND AGRICULTURAL MATERIAL | 25388000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF MEDICINE,LABARATORY EQUIPMENT ,HOSPITAL SUPPLIES,DENTAL SUPPLIES & MEDICAL GASES | LGA/049/G/2017/2018/20 | SUPPLY OF MEDICINE,LABARATORY EQUIPMENT ,HOSPITAL SUPPLIES,DENTAL SUPPLIES & MEDICAL GASES | 649500672 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
TOTAL |  |  | 1036100463.96
NON CONSULTANCE SERVICES
PROVISION OF MOTOR VEHICLE MAINTANANCE, WATER CRAFTS | LGA/049/G/2017/2018/01 | PROVISION OF MOTOR VEHICLE MAINTANANCE, WATER CRAFTS | 886726381 | SS-TEMESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Actual
PROVISION OF SEWAGE SERVISES | LGA/049/G/2017/2018/02 | PROVISION OF SEWAGE SERVISES | 11150000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF OUTSOURCING COSTS (INCLUDES CLEANING AND SECURITY SERVICES | LGA/049/G/2017/2018/03 | PROVISION OF OUTSOURCING COSTS (INCLUDES CLEANING AND SECURITY SERVICES | 1200000 | NCT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2/10/2017 | 6/10/2017 | 8/10/2017 | 22/10/2017 | 2/11/2017 | 5/11/2017 | 12/11/2017 | 19/11/2017 | 1200000 | 22/11/2017 | 22/11/2017 | Plan
Actual
PROVISION OF PHOTOCOPY AND PRINTING SERVICES | LGA/049/G/2017/2018/04 | PROVISION OF PHOTOCOPY AND PRINTING SERVICES | 31830000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF HIRING TRAINNING/ CONFERECE FACILITIES & ADVERTISIMENT SERVISES | LGA/049/G/2017/2018/05 | PROVISION OF HIRING TRAINNING/ CONFERECE FACILITIES & ADVERTISIMENT SERVISES | 5370000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
ADVERTISIMENT & PUBLICATION | LGA/049/G/2017/2018/06 | ADVERTISIMENT & PUBLICATION | 13600000 | Quotation | 12/05/2017 | 7/05/2017 | 9/05/2017 | 12/05/2017 | 25/5/2017 | 05/06/2017 | 08/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF FOOD & REFRESHMENT SERVISES | LGA/049/G/2017/2018/07 | PROVISION OF FOOD & REFRESHMENT SERVISES | 85417280 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
PROVISION OF FUMIGATION SERVICES | LGA/049/G/2017/2018/08 | PROVISION OF FUMIGATION SERVICES | 1500000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
TOTAL |  |  | 1036793661
CONSULTANCE SERVICES
PROVISION OF VALUATION | LGA/049/G/2017/2018/01 | PROVISION OF VALUATION | 86011208 | NCT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2/10/2017 | 6/10/2017 | 8/10/2017 | 22/10/2017 | 2/11/2017 | 5/11/2017 | 12/11/2017 | 19/11/2017 | 1200000 | 22/11/2017 | 22/11/2017 | Plan
Actual
TOTAL |  |  | 86011208 | [19 empty] | Plan
GRAND TOTAL /GOODS/NON-CONSULT/CONSULTANCY | [22 empty] | Actual
Plan
WORKS | [22 empty] | Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/01 | Makanya chankoko junction-Mvungwe,Hedaru, Ruvu ,Makanya Chankoko | 160000000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/02 | Bombo,Mpiran,kadando,maore, vuje | 74200000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/03 | Ishinde,Vumari, Same mjini | 113000000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/04 | Ruvu-Mferejini,Majevu-Dido-Njoro,minyala-Mbono, Mgagao na dengude | 71000000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/05 | Saweni-Gavao-Bwambo,Suji,,Mweteni-Hedaru,Makasa,Kirangare | 97000000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/06 | Kisiwani -Msindo,Mhezi Mbuyuni-Marindi,Mwerera -kisesa, Ijinyu Kamadufa | 88630000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/07 | Parane-Kitubwa -Kirongwe, Mpinji- Kiwandani- Manga- Chalinze and ndolwa kambeni- mshiwi | 54600000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/08 | Ndungu Makokane and Kalemawe- Karamba-Mgandu | 53000000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
| LGA/049/W/2017/2018/09 | Kidenge- Mwala, Hedaru- vunta Myamba and Vunta - Kidunda | 63800000 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
WATER WELL MAINTANANCE | LGA/049/W/2017/2018/10 | Maintanance of water and wells and schemes in Makokane, Kirore,Vugwama and Hedaru Village (Pipe and fittings) | 642996042 | NCT | 220/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 7/9/2017 | 10/09/2017 | 13/09/2017 | 26/09/2017 | 28/09/2017 | 08/10/2017 | 15/10/2017 | 22/10/2017 | 160000000 | 25/10/2017 | 25/10/2017 | Plan
Actual
TOTAL | [22 empty] | Plan
OBJECTIVE | WORKS | WORKS | WORKS | UNIT OF MEASURE | UNIT COST | NO OF UNITS | APPROVED ESTIMATES | CATEGORY | MTF PAGE NO
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/01 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF CHANKOKO JUNCTION - MVUNGWE, HEDARU - RUVU, MAKANYA - CHANKOKO ROADS | Lumpsum | 160000000 | 1 | 160000000 | W | 104
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/02 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF MPIRANI - BOMBO, MPIRANI-KADANDO, AND MAORE - VUJE ROADS | Lumpsum | 74200000 | 1 | 74200000 | W | 103
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/03 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF ISHINDE - VUMARI, SAME TOWN ROADS | Lumpsum | 113000000 | 1 | 113000000 | W | 103
DO2DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/04 ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF SAME - RUVU - MFEREJINI, MAJEVU - DIDO - NJORO, MINYALA - MBONO – MGAGAO, AND DENGUDE-DIDO ROADS | 511B | Routine Maintainance/Spot Improvement/Periodic Maintenance roads of Same - Ruvu - Mferejini 14Km, Majevu - Dido - Njoro 10Km, Minyala - Mbono - Mgagao 4Km and Dengude-Dido 3Km | Lumpsum | 71000000 | 1 | 71000000 |  | 103
DO2DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/06 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF SAWENI - GAVAO - BWAMBO, SUJI -MWETENI AND HEDARU-MAKASA-KIRANGARE ROADS | Lumpsum | 97000000 |  | 63800000 | W | 103
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/08 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF KISIWANI - MSINDO, MWEMBE -MHEZI, MBUYUNI-MARINDI, MWERERA-KISESA, IJINYU-KAMADUFA ROADS. | Lumpsum | 88630000 | 1 | 88630000 | W | 103
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/09 |  | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF PARANE-KITUBWA-KIRONGWE-MPINJI, KIWANDANI-MANG'A-CHALINZE AND NDOLWA-KAMBENI-MSHIWI ROADS |  | 54600000 | 1 | 54600000 | W | 103
DO1DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/10 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF NDUNGU-MAKOKANE AND KALEMAWE-KARAMBA-MGANDU ROADS | Lumpsum | 53000000 | 1 | 53000000 | W | 103
DO2DO1/DO1DO2 | TENDER NO. LGA/049/W/2017/2018/07 | 511B | ROUTINE MAINTENANCE/SPOT IMPROVEMENT/PERIODIC MAINTENANCE OF KIDENGE - MWALA, HEDARU-VUNTA-MYAMBA AND VUNTA –KIDUNDA ROADS | Lumpsum | 63800000 | 1 | 63800000 | W | 103
| TOTAL |  |  |  | 775230000
PIPES AND FITTINGS & WATER WELLS
D01D01/D01D02 | TENDER NO LGA/049/W/2017/2019/11 | 510A | MAINTENANCE OF WATER WELLS AND SCHEMES IN MAKOKANE, KIRORE, VUGWAMA AND HEDARU VILLAGES (PIPE & FITTINGS) | Lumpsum | 642996042 | W | 642996042 | W | 103
| GRAND TOTAL |  |  |  | 1418226042
| TOTAL APP |  | 3577131375

## APP-GNCONS-IU
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INTERNAL USE
Name of the Procuring Entity:
Financial Year:
Description* | Basic Data | [5 empty] | Gen. Proc Notice Advert | Request for Expression of Interest |  |  |  | Preparation of RFP Documents |  | Invitation of proposals and approval for award | [8 empty] | Contract Finalization |  |  | Plan vs. Actual
| Tender No. | Lot Number | Estimated Amount in Tshs '000 | Procurement Method | Selection Method | Contract Type |  | Invitation |  | Evaluation |  |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F)
[8 empty] | Invitation Date | Closing-Opening | Submission Eval. Rpt | Approval of Shortlist | Prep & Submission by PMU | Approval by TB | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | Approval of Evaluation Report (T) | Opening Financial Proposals | Submission Eval. Report (T) (F) | Approval Eval Report (T) (F) | Notice of intention to award Date | Vetting/ Ratification of contracts | Contract Amount in Tshs '000 | Contract award | Contract Signature
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Total Cost | [25 empty] | Plan
Actual

## APP-GNCONS-PPRA
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - SUBMISSION TO PPRA
Name of the Procuring Entity:
Financial Year:
Description* | Tender No. | Lot Number | Estimated Amount in Tshs '000 | Procurement Method | Gen. Proc Notice Advert | PRE-QUALIFICATION |  |  |  | Invitation of Tenderz and approval for award
[6 empty] | Invitation Date | Closing-Opening | Approval of Shortlist | Notification Date | Invitation Date | Submission/ Opening Date | Approval Eval Report (T) (F) | Notice of intention to award Date | Vetting/ Ratification of contracts | Notification Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 12 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SUPPLY OF OFICE CONSUMABLE AND COMPUTER ACCESSORY

## APP submissin ppra 2017-2018
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - SUBMISSION PPRA
Name of Procuring Entity:
FINANCIAL YEAR 2017-2018
Description | Tender No. | Lot Number | BASIC DATA |  | Gen. Proc Notice Advert |  |  | PRE-QUALIFICATION | Invitation for Tenders and Evaluation |  |  |  |  | Contract Finalization | Plan vs. Actual
[6 empty] | INVITATION |  | EVALUATION | Invitation for Tenderding |  | Tender Evaluation and approval of award
|  |  | Estimated Amount in '000 Tshs | Procurement Method |  | Invitation Date | Closing-Opening | Notification date | Tender Invitation Date | Tender Closing-Opening | Aprove Eval Rpt | Notice of intention to award Date | Vetting/ Ratification of contracts | Notification date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
GOODS
SUPPLY OF OFICE CONSUMABLE AND COMPUTER ACCESSORY | LGA/049/G/2017/2018/01 | LOT I-Supply of office consumable | 86239273 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT-II-supply of Computr ,Fax macine Scana,Printer and accesory | 12969960 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF FUEL AND LUBRICANT | LGA/049/G/2017/2018/02 | LOT I-Supply of diesel | 169797338.99 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT II- Supply of kerosine | 1076600 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA
SUPPLY OF FUEL |  | LOT III- Supply of Petrol | 29635348 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT IV- Supply of lubricant | 400000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF BUILDING MATERIA ,CLEAN SUPPLIES, AND PROTECTIVE GEAR | LGA/049/G/2017/2018/03 | LOT-I Supply of building material | 196376463 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
|  | LOT-II Supply of Clean material | 18958992 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF TRAINNING MATERIALS | LGA/049/G/2017/2018/04 | LOT -I SUPPLIES OF TRAINNING MATERIALS | 5392650 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF TYRE, BATTERY, SPARE PART & ELECTRONICS/ELECTRICAL PARTS | LGA/049/G/2017/2018/05 | SUPPLY OF TYRE, BATTERY, SPARE PART & ELECTRONICS/ELECTRICAL PARTS | 18400000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF UNIFORM AND SPORTING SUPPLIES | LGA/049/G/2017/2018/06 | SUPPLY OF UNIFORM AND SPORTING SUPPLIES | 20910000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLY OF FUNITURE & FITTINGS | LGA/049/G/2017/2018/07 | LOT I-SUPPLY OF FUNITURE & FITTINGS | 24133136 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF INFORMATION, COMMUNICATION & TECHNOLOGY EQUIPMENTS | LGA/049/G/2017/2018/08 | SUPPLIES OF INFORMATION, COMMUNICATION & TECHNOLOGY EQUIPMENTS | 9188533.96 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF DESK TABLE AND CHAIR | LGA/049/G/2017/2018/09 | SUPPLIES OF DESK TABLE AND CHAIR | 12500000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
PROVISION OF PROTECTIVE CLOTHEING FOOTWEAR AND GEARS | LGA/049/G/2017/2018/10 | PROVISION OF PROTECTIVE CLOTHEING FOOTWEAR AND GEARS | 1000000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
SUPPLIES OF SPECIALIZED EQUIPMENT & SMALL TOOLS | LGA/049/G/2017/2018/11 | SUPPLIES OF SPECIALIZED EQUIPMENT & SMALL TOOLS | 44829000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF TECHNICAL MATERIALS | LGA/049/G/2017/2018/12 | SUPPLIES OF TECHNICAL MATERIALS | 3550000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF NEWSPAPER & MAGAZINES AND BOOKS,REFERENCES & PERIODIC BOOKS | LGA/049/G/2017/2018/13 | SUPPLIES OF NEWSPAPER & MAGAZINES AND BOOKS,REFERENCES & PERIODIC BOOKS | 1979722 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF ARMS & AMMUNATIONS | LGA/049/G/2017/2018/14 | SUPPLIES OF ARMS & AMMUNATIONS | 500000 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLIES OF MOTORCLE /MOTOR VEHICLE | LGA/049/G/2017/2018/15 | SUPPLIES OF MOTORCLE /MOTOR VEHICLE | 168000000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF PHOTOGRAPHIC EQUIPMENT | LGA/049/G/2017/2018/16 | SUPPLY OF PHOTOGRAPHIC EQUIPMENT | 20099900 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF TV AND RADIO EQUIPMENT AND PULICITY | LGA/049/G/2017/2018/17 | SUPPLY OF TV AND RADIO EQUIPMENT AND PULICITY | 4200000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF VETINARY , SEEDS, AND AGRICULTURAL MATERIAL | LGA/049/G/2017/2018/18 | SUPPLY OF VETINARY , SEEDS, AND AGRICULTURAL MATERIAL | 6138000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
SUPPLY OF MEDICINE,LABARATORY EQUIPMENT ,HOSPITAL SUPPLIES,DENTAL SUPPLIES & MEDICAL GASES | LGA/049/G/2017/2018/20 | SUPPLY OF MEDICINE,LABARATORY EQUIPMENT ,HOSPITAL SUPPLIES,DENTAL SUPPLIES & MEDICAL GASES | 418200672 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
TOTAL |  |  | 1274408588.95
NON CONSULTANCE SERVICES
PROVISION OF MOTOR VEHICLE MAINTANANCE, WATER CRAFTS | LGA/049/G/2017/2018/01 | PROVISION OF MOTOR VEHICLE MAINTANANCE, WATER CRAFTS | 581326381.68 | SS-TEMESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Actual
PROVISION OF SEWAGE SERVISES | LGA/049/G/2017/2018/02 | PROVISION OF SEWAGE SERVISES | 11150000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF OUTSOURCING COSTS (INCLUDES CLEANING AND SECURITY SERVICES | LGA/049/G/2017/2018/03 | PROVISION OF OUTSOURCING COSTS (INCLUDES CLEANING AND SECURITY SERVICES | 1200000 | NCT | N/A | N/A | N/A | N/A | 8/10/2017 | 22/10/2017 | 2/11/2017 | 12/11/2017 | 19/11/2017 | 1200000 | Plan
Actual
PROVISION OF PHOTOCOPY AND PRINTING SERVICES | LGA/049/G/2017/2018/04 | PROVISION OF PHOTOCOPY AND PRINTING SERVICES | 31830000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF HIRING TRAINNING/ CONFERECE FACILITIES & ADVERTISIMENT SERVISES | LGA/049/G/2017/2018/05 | PROVISION OF HIRING TRAINNING/ CONFERECE FACILITIES & ADVERTISIMENT SERVISES | 5370000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
ADVERTISIMENT & PUBLICATION | LGA/049/G/2017/2018/06 | ADVERTISIMENT & PUBLICATION | 13600000 | Quotation | 12/05/2017 | 12/05/2017 | 25/5/2017 | 29/05/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
PROVISION OF FOOD & REFRESHMENT SERVISES | LGA/049/G/2017/2018/07 | PROVISION OF FOOD & REFRESHMENT SERVISES | 85417280 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
PROVISION OF FUMIGATION SERVICES | LGA/049/G/2017/2018/08 | PROVISION OF FUMIGATION SERVICES | 1500000 | Min Competion | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | GPSA | Plan
Actual
TOTAL |  |  | 731393661.68
CONSULTANCE SERVICES
PROVISION OF VALUATION | LGA/049/G/2017/2018/01 | PROVISION OF VALUATION | 86011208 | NCT | N/A | N/A | N/A | N/A | 8/10/2017 | 22/10/2017 | 2/11/2017 | 12/11/2017 | 19/11/2017 | 86011208 | Plan
Actual
TOTAL |  |  | 86011208 | [11 empty] | Plan
Actual
Plan
WORKS | [14 empty] | Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/01 | Makanya chankoko junction-Mvungwe,Hedaru, Ruvu ,Makanya Chankoko | 160000000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 160000000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/02 | Bombo,Mpiran,kadando,maore, vuje | 74200000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 74200000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/03 | Ishinde,Vumari, Same mjini | 113000000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 113000000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/04 | Ruvu-Mferejini,Majevu-Dido-Njoro,minyala-Mbono, Mgagao na dengude | 71000000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 71000000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/05 | Saweni-Gavao-Bwambo,Suji,,Mweteni-Hedaru,Makasa,Kirangare | 97000000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 97000000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/06 | Kisiwani -Msindo,Mhezi Mbuyuni-Marindi,Mwerera -kisesa, Ijinyu Kamadufa | 88630000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 88630000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/07 | Parane-Kitubwa -Kirongwe, Mpinji- Kiwandani- Manga- Chalinze and ndolwa kambeni- mshiwi | 54600000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 54600000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/08 | Ndungu Makokane and Kalemawe- Karamba-Mgandu | 53000000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 53000000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/09 | Routine /spot improvenment /periodic maintanance maintanace of Mgwasi, Bangalala- chome 10km and chome- ikokoa 10km | 56500000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 56500000 | Plan
Actual
ROAD MAINTANANCE | LGA/049/W/2017/2018/10 | Kidenge- Mwala, Hedaru- vunta Myamba and Vunta - Kidunda | 63800000 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 63800000 | Plan
Actual
WATER WELL MAINTANANCE | LGA/049/W/2017/2018/10 | Maintanance of water and wells and schemes in Makokane, Kirore,Vugwama and Hedaru Village (Pipe and fittings) | 642996042 | NCT | 220/6/2017 | N/A | N/A | N/A | 13/09/2017 | 26/09/2017 | 28/09/2017 | 15/10/2017 | 22/10/2017 | 642996042 | Plan
Actual
TOTAL |  |  | 1474726042 | [11 empty] | Plan
SAME DISTRICT COUNCIL GENERAL PROCUREMENT FOR FYR 2017/2018 The government of United Republic of Tanzania has set a side fund for various operation of Same District Council for the finacial year 2017/2018.The council now notifies potential bidders of the procurement oppotunites to be advitersed soon.Potential bidders may obtained information from the office of the secretary of the Tender board at the council. PROCUREMENT PLAN FOR WORKS,GOOD,COUNSULTANCY AND NON COUNSULTANCY SERVICES -EXTERNAL USE Name of procuring entity: SAME DISTRICT COUNCIL finacial year 2017/2018